## Topic & Keyword
Topic and Keyword
(*) Dựa trên tài liệu PMBOK 6
Lesson | Topic | Present PIC (group) | Keyword | Note | Q&A (nếu có)
2 | Overall: Framework + Process (Chapter 1-3) | -
| Projects Relationship of Project, Program, Portfolio, and Operations Management Tailoring Project Management Business Documents | 1 | What is Project, Program, Portfolio,Operations Relationship of Project, Program, Portfolio, and Operations Management ORGANIZATIONAL PROJECT MANAGEMENT (OPM) Tailoring Project business case, Project benefits management plan, Project charter and project management plan | chú ý: keywords không chia đúng theo topic mà phân ngẫu nhiên
| THE ENVIRONMENT IN WHICH PROJECTS OPERATE Enterprise Environmental Factors Organizational Process Assets Organizational Systems | 2 | Project life cycle, Project phase, Phase gate, Project management processes,Project Management Process Group, Project Management Knowledge Area Work performance data (WPD), Work performance information (WPI), Work performance reports (WPR)
| THE ROLE OF THE PROJECT MANAGER Definition of a Project Manager The Project Manager’s Sphere of Influence | 3 | Enterprise Environmental Factors (EEF): External, Internal Organizational Process Assets (OPA): Processes, Policies and Procedures, Corporate Knowledge Base Organizational structure: Functional organization, Projectized organization, Matrix PROJECT MANAGEMENT OFFICE (PMO)
| THE ROLE OF THE PROJECT MANAGER Project Manager Competences Performing Integration | 4 | Function Manager, Operations managers, Project manager Project manager competences MANAGEMENT VS. LEADERSHIP
3 | Scope Management | -
| 5.1 Plan Scope Management | 2 | product scope, project scope, wbs, work pakage, rtm, iteration, define scope, | chú ý: keywords không chia đúng theo topic mà phân ngẫu nhiên
| 5.2 Collect Requirements | 3 | Project scope statement, Scope baseline: WBS, WBS dictionary, Project scope statement, Work package, Planning package.
| 5.3 Define Scope 5.4 Create WBS | 4 | Project scope description, Deliverables, Acceptance criteria, Project exclusion
| 5.5 Validate Scope 5.6 Control Scope | 1 | Validate scope, Scope creep, Inspection, Variance analysis,
4 | Schedule Management | -
| 6.1 Plan Schedule Management 6.2 Define Activities | 3 | Schedule compressing: fast track, crashing,​ On-demand scheduling​ Resource optimizing: smoothing, levelling​ Agile release planning​ rolling wave planning​ pull-based scheduling​ Kanban board / Kanban system​ Milestone​ | chú ý: keywords không chia đúng theo topic mà phân ngẫu nhiên
| 6.3 Sequence Activities 6.4 Estimate Activity Durations | 4 | Scheduling network diagram/ Schedule model/scheduling method/ scheduling data/ Schedule basline​ PDM/ ADM​ PDM/AON​ Dependencies ​ 4 logical Relationships​ Leads/ lags​ Analog estimating/ bottom up estimating/ parametric estimating/ three points estimating​ Sprint planning meetings Iteration planning meetings​
| 6.5 Develop Schedule | 1 | Monte Carlo analysis​ Path convergence​ Critical Path Method-CPM/ Critical Chain Method -CCM​ ROM (Rough order of magnitude )/ Definitive estimation ​ Project calendars​ SV/ SPI/ ​ Forward pass/ backward pass​ Forecasting report​ PMIS​
| 6.6 Control Schedule | 2 | Critical Path​ Earn value analysis ​ Iteration burndown chart​ Peformance reviews​ Trend analysis​ Variance analysis ​ What – if scenario analysis​ Law of diminishing returns​ Parkison law​ Reserve analysis​
5 | Cost Management | -
| 7.1 Plan Cost Management | 4 | Analogous Estimating, Cost Aggreegation, Funding Limit Reconciliation
| 7.2 Estimate Costs | 1 | Project funding requirement, work performance data, cost forecasts
| 7.3 Determine Budget | 2 | Control Thresholds. Two Complete Performance Index, bottom up estimating
| 7.4 Control Costs | 3 | PMIS, Work Performance Information, EVM, Parametric Estimating
6 | Quality Management | -
| 8.1 Plan Quality Management | 1 | Quality vs Grade, Prevention vs Inspectation, Attribute Sampling vs Variable Sampling, Tolerances, Control limits | chú ý: keywords không chia đúng theo topic mà phân ngẫu nhiên
| 8.2 Manage Quality | 2 | Cost of quality (COQ), Cost of Conformance: Prevention Costs, Appraisal Costs, Cost of Nonconformance: Internal Failure Costs, External Failure Costs
| 8.2 Manage Quality | 3 | Benchmarking, Gold Plating, plan-do-check-act (PDCA) , Just in Time (JIT). SIPOC model, Root cause analysis (RCA), Affinity diagrams, Cause-and-effect diagrams (Fish bone diagram, 5-why diagram, ishikawa diagram), Scatter diagrams, Control charts
| 8.3 Control Quality | 4 | Statistical sampling, Design of experiments, Audits, Design for X, six-sigma, PROBLEM SOLVING, Continuous Improvement, Retrospectives, VERIFIED DELIVERABLES, WORK PERFORMANCE INFORMATION
7 | Integration Management | -
| 4.1 Develop Project Charter 4.2 Develop Project Management Plan | 2 | PV, NPV, IRR, Payback Period, Cost-Benefit Analysis, Opportunity Cost, Sunk Costs, Benefits management plan, business case, Accepted Deliverables​, close project, final report,
| 4.3 Direct and Manage Project Work 4.4 Manage Project Knowledge | 3 | Law of Diminishing Returns, Work performance data, Knowledge , explicit, tacit,Alternatives analysis, Root cause analysis,Trend analysis , Cost-benefit analysis, Earned value analysis, Variance analysis​, Work Performance Reports ,
| 4.5 Monitor and Control Project Work | 4 | Depreciation, Straight-line depreciation, Accelerated depreciation, Kickoff Meeting, Autocratic decision making​, Perform Integrated Change Control process, CCB , Corrective action, Preventive action​, change log,
| 4.6 Perform Integrated Change Control 4.7 Close Project or Phase | 1 | Change Management Plan, Configuration Management Plan, Change Control System, Configuration Management System, Work Authorization System, Detailed Process for Making Changes - 7 steps, Regression analysis​, Variance analysis​, Trend analysis​,
8 | Risk Management | -
| 11.1 Plan Risk Management 11.2 Identify Risks | 1 | Risk attitude, Risk appetite, Risk threshold, Risk register, Risk report , RISK TRIGGER, risk urgency assessment, unidentified risk | chú ý: keywords không chia đúng theo topic mà phân ngẫu nhiên
| 11.3 Perform Qualitative Risk Analysis 11.4 Perform Quantitative Risk Analysis | 2 | risk priority, Risk Averse, Tornado, sensitivity , contingency reserve, Contingency Plan and Fallback Plan, Sensitivity analysis, Watch list, contigency reserves va management reserves, Perform Qualitative Risk Analysis, Perform Quantitative Risk Analysis ,
| 11.5 Plan Risk Responses | 3 | five strategies to respond to positive risks: Escalate, Accept, Exploit, Enhance, and share,4strategies to respond to negtive risks: five strategies to respond to positive risks: Risk mitigation, Risk avoidance, Risk acceptance, Risk transference, , Residual risk, Secondary risks,
| 11.6 Implement Risk Responses 11.7 Monitor Risks | 4 | Risk mitigation, Risk avoidance, Risk acceptance, Risk transference, probability and impact matrix, individual risks và overall risks, risk owner, risk response, risk workshop, Monte Carlo , RBS, risk audit, risk review, high level risk,
11 | Communications Management | -
| 10.1 Plan Communications Management | 4 | Comm requirements, comm technologies, political awareness, cultural awareness, public comm, mass comm, interative comm, intepersonal comm | chú ý: keywords không chia đúng theo topic mà phân ngẫu nhiên
| 10.2 Manage Communications | 1 | PMIS, comm channels, comm methods, push comm, pull comm, communication styles assessment
| 10.2 Manage Communications | 2 | comm models, Sender-receiver comm model: Encode/ transmit message/ decode/ acknowledge/ feedback Interative comm model: acknowledge-feedback response Hierarchical focus: Upward/Downward/Horizontal, comm types, Official/Unofficial, Formal or informal, Written and oral, Choice of media. Work performance data​, Work performance information​, work performance report
| 10.3 Monitor Communications | 3 | Progress report​, Status report​, Trend report​, Forecast report​, Variance report​, Earned value report, Meeting management, social media management, electronic communications management, and electronic project management tools
10 | Resource Management | -
| 9.1 Plan Resource Management 9.2 Estimate Activity Resources | 3 | Resource management methods: justin-time (JIT) manufacturing, Kaizen, Self-organizing teams, Virtual teams/distributed teams, Work breakdown structures (WBS), Organizational breakdown structure (OBS), Responsibility Assignment Matrix (RAM), Resource breakdown structure, RACI (responsible, accountable, consult, and inform) chart | chú ý: keywords không chia đúng theo topic mà phân ngẫu nhiên
| 9.3 Acquire Resources | 4 | pre-assignment, virtual teams, human resource, physical resource, negotiation, project team assignments, resource calendars
| 9.4 Develop Team | 1 | COLOCATION, Motivation Theory (Theory of X and Y, Maslow's Hierachy of Need, McClelland's Theory of Need), Negotiation, Team building, Tuckman ladder, RECOGNITION AND REWARDS
| 9.5 Manage Team 9.6 Control Resources | 2 | Conflict management, Emotional intelligence (EI), Influencing, Leadership, Halo Effect
11 | Procurement Management | -
| 12.1 Plan Procurement Management | 2 | Memorandum of Agreement (MOA), service level agreement (SLA), bid documents (RFP - request for proposal, RFI - request for information, or RFQ - request for quotation) , procurement statement of work - (SOW), terms of reference (TOR), Decentralized purchasing, Centralized purchasing | chú ý: keywords không chia đúng theo topic mà phân ngẫu nhiên
| 12.2 Conduct Procurements | 3 | Firm Fixed Price (FFP), Fixed Price Incentive Fee (FPIF), Fixed Price with Economic Price Adjustment (FPEPA), Cost Plus Fixed Fee (CPFF), Cost Plus Incentive Fee (CPIF), Cost Plus Award Fee (CPAF), Cost Plus Percentage of Costs (CPPC), Time and Material (T&M)
| 12.2 Conduct Procurements | 4 | Sharing ratio, Ceiling price, Sole source, Single source, bidder conference ,
| 12.3 Control Procurements | 1 | Claims administration, Terminate for cause, Terminate for convenience
12 | Stakeholder Management | -
| 13.1 Identify Stakeholders | 3 |  | chú ý: keywords không chia đúng theo topic mà phân ngẫu nhiên
| 13.2 Plan Stakeholder Engagement | 4
| 13.3 Manage Stakeholder Engagement | 1
| 13.4 Monitor Stakeholder Engagement | 2
13 | Agile & Scrum (part 1) | -
| The Agile manifesto | 4 | Agile methods and approaches ,Agile Manifesto: 4 core values, 12 principles, Agile Triangle | Nguồn tham khảo: ・Sách: PMI-ACP Exam Prep - Mike Griffiths.pdf ・Sách: PMI_Agile Practice Guide.pdf ・Google
| Scrum Theory | 1 | 3 Pillars: Transparency, Inspection, Adaptation
| Scrum Values | 2 | 5 values: Commitment, Focus, Openness, Respect, and Courage
| Scrum Artifacts | 3 | product backlog, sprint backlog, Increment, Definition of Done (DoD), Backlog Refinement
14 | Agile & Scrum (part 2) | -
| Scrum Events | 1 | The Sprint, Sprint Planning, Planning Pocker, Team Capacity, Velocity, Story Point, Daily Scrum, Sprint Review, Sprint Retrospective | Nguồn tham khảo: ・Sách: PMI-ACP Exam Prep - Mike Griffiths.pdf ・Sách: PMI_Agile Practice Guide.pdf ・Google
| The Scrum Team and accountabilities | 2 | Product Owner (PO), Scrum Master (SM), Developers (Dev Team), Self Organizing, Generilizing Specialist
| The Scrum Team and accountabilities | 3 | Servant Leader
| Terms and tools used in Agile and Scrum projects | 4 | Scrum of Scrum (Scaled Agile), Burndown chart, Burn-up chart, Velocity Chart, Technical Debt, Minimum Viable Product (MVP)
15 | Agile & Scrum (part 3) | -
| Lean | 2 | Core principles, 7 wastes | Nguồn tham khảo: ・Sách: PMI-ACP Exam Prep - Mike Griffiths.pdf ・Sách: PMI_Agile Practice Guide.pdf ・Google
| Kanban | 3 | 5 principles, Pull system, WIP limits
| Extreme Programming (XP) | 4 | Core practices
| Extreme Programming (XP) | 1 | Core values, Team roles
Note on G4: Đặt câu hỏi trước để mentor chuẩn bị cũng như tiết kiệm time cho buổi học, mentor sẽ trả lời trong buổi học